## Website Tracker
Week | Focus Area | Sample Tasks | Status | Deadline | Notes
1 | Project Setup & UI Design | Set up repo, basic pages (Home, About, Contact) | Not Started | 2025-05-19
2 | Registration Forms + Login | Student & Tutor forms, role-based login | Not Started | 2025-05-26
3 | Dashboards | Dashboards for student, tutor, admin | Not Started | 2025-06-02
4 | Attendance + Fee Management | Attendance tracking, fee management UI | Not Started | 2025-06-09
5 | Study Materials + Timetable | Upload/download study materials, create timetable | Not Started | 2025-06-16
6 | Notifications + Testimonials | Add testimonial section, notifications (SMS/email) | Not Started | 2025-06-23
7 | Blog + SEO + Contact | Blog section, contact form, SEO basics | Not Started | 2025-06-30
8 | Security + Final Touches | Add OTP login, deploy website, testing | Not Started | 2025-07-07